## How to use
Failure Mode Register
Andre Gemelli. Generated 2026-08-25 08:30:18 (America/Sao_Paulo, UTC-03:00).
What this is for
A pre-mortem produces a list of ways a plan can fail. That list is worthless if it lives in a meeting note. This register is where it lives instead, and where it is checked against what actually happened. The register is the memory; the pre-mortem is only the input.
The method, thirty minutes
1. Setup, 2 min. State the plan and a specific date. "It is 2027-03-31. The Pelotas pilot has been cancelled and the client has gone to a competitor." Failure is stipulated as fact, not proposed as a risk.
2. Silent independent writing, 7 min. Everyone writes their own account of what happened. Silence is not optional. Any discussion first anchors the room and collapses the diversity of failure paths, which is the entire value of the exercise.
3. Round robin, 12 min. One cause each, going round until exhausted. No debate. No defending the plan. No "we already have a mitigation for that". Capture only.
4. Rank, 5 min. Plausibility times cost. Not probability alone. A low-probability failure that kills the account outranks a likely failure that costs a week.
5. Convert, 4 min. Top three become probes with named owners and dates. Everything else lands in the register at status Open.
Two rules that decide whether this works
Run it while the plan can still change. A pre-mortem after the decision is emotionally locked in is theatre, and it generates a register nobody reads.
The author of the plan writes silently like everyone else and speaks last. Letting the author go first re-anchors the room to the optimistic case.
How to fill it in
Cells with a pale yellow fill are yours to type into. Everything else is calculated and should be left alone.
Plausibility and Cost are both scored 1 to 5. Score is calculated as the product, so it runs 1 to 25.
Status moves through: Open, Probed, Mitigated, Accepted, Materialised, Closed. Accepted is a legitimate destination. Not every failure mode is worth spending on, but the decision to accept should be recorded rather than implied by silence.
Each sheet carries one example row in grey italic. Delete it once you have real entries.
The number that matters
On the Summary sheet, watch "Materialised without having been probed". Every entry in that count is a failure the method saw coming and the organisation did nothing about. That figure is the honest measure of whether this register is a working instrument or a filing cabinet.
Formatting rule for anything derived from this file
No em-dashes and no en-dashes, anywhere, in any document that comes out of this workbook. Ranges are written with the word "to".

## Pre-Mortem Capture
Pre-Mortem Capture Sheet
One session per copy of this sheet. Template generated 2026-08-25 08:30:18.
Session date | 2026-09-15
Engagement or plan | Pelotas fare collection pilot, phase 2
Stipulated failure date | 2027-03-31
Stipulated failure statement | The pilot has been cancelled and the client has gone to a competitor.
Facilitator | Andre Gemelli
Participants | Delivery, integration, commercial, client-side sponsor
Cynefin domain of the plan | Complex
Failure paths, captured in round robin. No debate at this stage.
# | Failure path, written as history | Category | Who would see it first | Plausibility 1 to 5 | Cost 1 to 5 | Score | Rank
1 | Bank-side certification slots were booked out and the integration sat finished but uncertified for nine weeks. The client read the silence as drift. | External dependency | Integration lead | 4 | 5 | 20 | 1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Aim for at least six distinct paths before you stop. A pre-mortem that produces three has not gone past the obvious.
Top three by score become probes with a named owner and a date. Transfer every row to the Register sheet before closing this session.

## Register
Running Failure Mode Register
Every failure path from every pre-mortem, and what happened to it. Template generated 2026-08-25 08:30:18.
ID | Date raised | Engagement | Failure path | Category | Plaus 1 to 5 | Cost 1 to 5 | Score | Status | Owner | Probe or mitigation | Due | Outcome | Date closed | Was it probed
FM-001 | 2026-09-15 | Pelotas pilot | Bank-side certification slots were booked out and the integration sat finished but uncertified for nine weeks. The client read the silence as drift. | External dependency | 4 | 5 | 20 | Probed | Integration lead | Request indicative certification slot dates from the bank before committing to a go-live date. Two week probe. | 2026-09-29 | Slots confirmed at 11 weeks out. Go-live date moved before it was published. | 2026-10-02 | Yes

## Summary
Register Summary
Calculated. Nothing on this sheet is typed. Template generated 2026-08-25 08:30:18.
Entries by status
Status | Count
Open | 0
Probed | 1
Mitigated | 0
Accepted | 0
Materialised | 0
Closed | 0
Total logged | 1
The number that matters
Materialised without having been probed
0 | Each one is a failure this method saw coming and the organisation did nothing about. If this is not zero, the register is a filing cabinet rather than an instrument.
Highest scoring entries still open
0 | Open entries scoring 16 or above out of 25. Anything sitting here has been named as both plausible and expensive, and has had nothing done about it.
Coverage
Distinct engagements with at least one entry | 1
Mean score of all logged entries | 20
Entries accepted without mitigation | 0
Generated 2026-08-25 08:30:18 (America/Sao_Paulo, UTC-03:00). Andre Gemelli.